## Sheet1
Project start date | 2024-09-27 | [7 empty] | 2024 | [12 empty] | 2025
Project Name: | HCI meets AI | [7 empty] | 2024-10-04 |  |  |  | 2024-11-08 |  |  |  |  | 2024-12-13 |  |  |  | 2025-01-17 |  |  |  |  | 2025-02-07 |  |  |  | 2025-03-14 |  |  |  | 2025-04-11 |  |  |  | 2025-05-09 |  |  |  |  | 2025-06-13 |  |  |  | 2025-07-11
 | time axis 2024-09-27 to 2025-07-25
| # | Activity | Assigned To | Start | End | Days | Status
| 1 | Understanding the Scope |  | 2024-09-27 | 2024-09-30 | 3 | Complete
| 2 | Introduction to the thesis |  | 2024-09-28 | 2024-10-03 | 5 | Complete
| 3 | Read the main document |  | 2024-09-30 | 2024-10-11 | 11 | Complete
| 4 | Read the 10 research papers associated to the intro |  | 2024-10-04 | 2024-10-06 | 2 | Complete
| 5 | Read papers on semantic scholar related to conversation + gaze |  | 2024-10-05 | 2024-10-14 | 9 | Complete
| 6 | Read papers on semantic scholar related to words + gaze |  | 2024-10-08 | 2024-10-24 | 16 | Complete
| 7 | Read papers on semantic scholar related to gesture + gaze |  | 2024-10-14 | 2024-10-18 | 4 | Complete
| 8 | Discover what the available datasets |  | 2024-10-16 | 2024-10-24 | 8 | Complete
| 9 | Download the AMI Corpus dataset |  | 2024-10-19 | 2024-11-06 | 18 | In progress
| 10 | Download the AV Café dataset |  | 2024-10-26 | 2024-10-29 | 3 | Blocked
| 11 | Check what the parameters are in AMI |  | 2024-10-27 | 2024-11-04 | 8 | Complete
| 12 | Check what the parameters are in AV Café |  | 2024-10-30 | 2024-11-10 | 11 | Complete
| 13 | Revisit our main research question |  | 2024-11-03 | 2024-11-05 | 2 | Complete
| 14 | Develop a summary mindmap |  | 2024-11-04 | 2024-11-09 | 5 | In progress
| 15 | Establish the research question: What keywords in a meeting transcript grab gaze attention? |  | 2024-11-06 | 2024-11-25 | 19 | Complete
| 16 | Review prior research on spontaneous eyeblink rate (SEBR) and its relevance to attention. |  | 2024-11-13 | 2024-11-17 | 4 | Complete
| 17 | Summarize findings on gaze behavior in conversations (turn-taking, speaker roles). |  | 2024-11-15 | 2024-11-20 | 5 | Not started
| 18 | Investigate how gaze shifts relate to listener engagement and disengagement. |  | 2024-11-17 | 2024-12-04 | 17 | Complete
| 19 | Explore datasets like AMI Corpus and AV Cafe for suitability. |  | 2024-11-24 | 2024-11-26 | 2 | Complete
| 20 | Develop hypotheses on keywords influencing gaze shifts. |  | 2024-11-25 | 2024-12-01 | 6 | Complete
| 21 | Designing the methodology |  | 2024-11-27 | 2024-12-14 | 17 | Complete
| 22 | Select a suitable dataset (e.g., AMI Corpus, AV Cafe). |  | 2024-12-04 | 2024-12-07 | 3 | Complete
| 23 | Identify scenarios with single and multiple listeners for analysis. |  | 2024-12-05 | 2024-12-14 | 9 | Complete
| 24 | Define gaze metrics: fixation duration, saccade frequency, and direction. |  | 2024-12-08 | 2024-12-27 | 19 | Complete
| 25 | Annotate transcripts with keywords and emotional attributes. |  | 2024-12-15 | 2024-12-19 | 4 | Complete
| 26 | Plan for emotion and valence integration into the analysis. |  | 2024-12-17 | 2024-12-22 | 5 | Complete
| 27 | Design comparative studies across topics (e.g., politics vs. economics). |  | 2024-12-19 | 2025-01-04 | 16 | Complete
| 28 | Establish metrics for evaluating attention shifts (e.g., percentage of listeners shifting gaze). |  | 2024-12-25 | 2024-12-28 | 3 | Complete
| 29 | Define a validation method for findings (e.g., cross-dataset comparison). |  | 2024-12-26 | 2025-01-01 | 6
| 30 | Pre-process the data |  | 2024-12-28 | 2025-01-12 | 15
| 31 | Extract gaze-related data from chosen datasets. |  | 2025-01-03 | 2025-01-06 | 3
| 32 | Synchronize transcription and gaze recordings using timestamps. |  | 2025-01-04 | 2025-01-12 | 8
| 33 | Clean datasets to remove noisy or irrelevant data. |  | 2025-01-07 | 2025-01-17 | 10
| 34 | Annotate gaze events (if in some files with small data not included) |  | 2025-01-11 | 2025-01-14 | 3
| 35 | Tag keywords by type (e.g., conjunctions, task-related, emotional). |  | 2025-01-12 | 2025-01-18 | 6
| 36 | Annotate emotional features (valence, arousal) where available. |  | 2025-01-14 | 2025-02-01 | 18
| 37 | Organize data for single (keep it simple first Mihai advice) and then multi-person scenarios. |  | 2025-01-21 | 2025-01-25 | 4
| 38 | Analyze the data |  | 2025-01-23 | 2025-01-31 | 8
| 39 | Perform statistical analysis on gaze shifts for specific keywords. |  | 2025-01-26 | 2025-02-06 | 11
| 40 | Compare gaze responses across topics (e.g., politics vs. economics). |  | 2025-01-30 | 2025-02-02 | 3
| 41 | Evaluate gaze synchronization between speaker and listeners. |  | 2025-01-31 | 2025-02-05 | 5
| 42 | Explore relationships between emotions (e.g., valence) and gaze. |  | 2025-02-02 | 2025-02-19 | 17
| 43 | Visualize findings with heatmaps of a transcript color coded. |  | 2025-02-09 | 2025-02-11 | 2
| 44 | Identify high-impact keywords that consistently draw attention. |  | 2025-02-10 | 2025-02-15 | 5
| 45 | Cross-validate findings with multiple datasets. |  | 2025-02-12 | 2025-03-03 | 19
| 46 | Select AI model |  | 2025-02-19 | 2025-02-21 | 2
| 47 | Review model types: Explore models like Random Forest, LSTM, Transformers, etc. |  | 2025-02-20 | 2025-02-28 | 8
| 48 | Evaluate features: Define input features (e.g., keyword type, gaze metrics) and output predictions. |  | 2025-02-23 | 2025-03-08 | 13
| 49 | Benchmark models: Compare use cases and computational requirements for different models. |  | 2025-02-28 | 2025-03-02 | 2
| 50 | Select models for testing: Choose 2–3 candidate models to experiment with. |  | 2025-03-01 | 2025-03-07 | 6
| 51 | Identify preprocessing requirements: Feature scaling or embedding generation if required. |  | 2025-03-03 | 2025-03-14 | 11
| 52 | Train AI model |  | 2025-03-07 | 2025-03-11 | 4
| 53 | Prepare training data for AMI Corpus: Split data into training, validation, and test sets (e.g., 70%-20%-10%). |  | 2025-03-09 | 2025-03-15 | 6
| 54 | Train the model: Use training data and optimize using hyperparameter tuning. |  | 2025-03-11 | 2025-03-21 | 10
| 55 | Validate model: Evaluate performance using metrics like accuracy, F1-Score, AUC-ROC, etc. |  | 2025-03-15 | 2025-03-19 | 4
| 56 | Analyze errors: Identify patterns in misclassified predictions and adjust features or preprocessing. |  | 2025-03-17 | 2025-03-26 | 9
| 57 | Iterate and refine: Incorporate feedback from validation to improve the model. |  | 2025-03-20 | 2025-03-30 | 10
| 58 | Save the trained model: Save configurations and document the training process. |  | 2025-03-24 | 2025-03-28 | 4
| 59 | Reiterate for AvCafe |  | 2025-03-26 | 2025-04-03 | 8
| 60 | Predict with AI model |  | 2025-03-29 | 2025-04-16 | 18
| 61 | Apply the model to new transcripts and gaze data. |  | 2025-04-05 | 2025-04-07 | 2
| 62 | Predict attention shifts for specific keywords and topics. |  | 2025-04-06 | 2025-04-12 | 6
| 63 | Compare predictions to actual gaze behaviors from datasets. |  | 2025-04-08 | 2025-04-22 | 14
| 64 | Use results to refine keyword annotations. |  | 2025-04-13 | 2025-04-15 | 2
| 65 | Explore predictions across different topics and emotional contexts. |  | 2025-04-14 | 2025-04-21 | 7
| 66 | Check and implement possibilities for fine tuning depending on each person |  | 2025-04-17 | 2025-04-28 | 11
| 67 | Organize all research findings into one place. |  | 2025-04-21 | 2025-04-25 | 4
| 68 | Documentation |  | 2025-04-23 | 2025-05-02 | 9
| 69 | Create a basic outline for the thesis (e.g., Introduction, Methodology, Results). |  | 2025-04-26 | 2025-05-12 | 16
| 70 | Write an introduction explaining the problem and our research goals. |  | 2025-05-02 | 2025-05-05 | 3
| 71 | Describe our methods: how we processed data, analyzed it, and trained models. |  | 2025-05-03 | 2025-05-09 | 6
| 72 | Summarize results with simple tables and graphs. |  | 2025-05-05 | 2025-05-15 | 10
| 73 | Discuss what our results mean and how they compare to other studies. |  | 2025-05-09 | 2025-05-12 | 3
| 74 | Write a conclusion summarizing our work and suggest next steps. |  | 2025-05-10 | 2025-05-19 | 9
| 75 | Proofread and edit the entire thesis for clarity and grammar. |  | 2025-05-13 | 2025-05-29 | 16
| 76 | Keep a log of all our experiments and their outcomes. |  | 2025-05-19 | 2025-05-22 | 3
| 77 | Use version control (e.g., Google Docs, Git) to track changes in our work. |  | 2025-05-20 | 2025-05-27 | 7
| 78 | Add extra materials (e.g., raw data, code, graphs) in an appendix. |  | 2025-05-23 | 2025-06-11 | 19
| 79 | Create a bibliography using citation tools like Zotero. |  | 2025-05-30 | 2025-06-03 | 4
| 80 | Submit our draft to our supervisor or peers for feedback. |  | 2025-06-01 | 2025-06-10 | 9
| 81 | Prepare a simple slide presentation for our thesis defense. |  | 2025-06-04 | 2025-06-20 | 16
| 82 | Write down challenges we faced and how we solved them. |  | 2025-06-10 | 2025-06-14 | 4
| 83 | Save our final data, models, and code in a secure folder or repository. |  | 2025-06-12 | 2025-06-13 | 1
Statuses
Not started
In progress
Blocked
Complete
Formulas:
End = [Start]+[Days]

## Chart
# | Tasks | Jan | Feb | Mar | Apr | May | Jun | Jul
1 | Literature Review
2 | Designing the methodology
3 | Data preprocess
4 | Data analysis
5 | AI model
6 | Documentation